## PSPH Project Plan (hidden)
Pregnancy Support Pathway Strategic Hub Project Timeline
| Activity | Due Date
|  | August | September | October | November | December
Task 1: Planning and Management | Project Planning
Confirm Committee membership
Send calendar invites through December
Hold bi-monthly check-in meetings for Project Committee
Project Launch
Finalize agenda and meeting materials
Share slides and background documents
Assign notetaking and follow-up tracking
Hold 90 minute project kickoff meeting
Document Review
Conduct background meetings
Develop Workplan
Incorporate feedback from committee
Circulate for internal review
Task 2: Vision and Planning | Submit work plan
Draft Framework for Stakeholder Engagement Sessions
Review existing engagement tools and frameworks
Identify stakeholders to include
Draft engagement goals and session formats
Internal team review of framework
Submit framework
Stakeholder Engagement Sessions
Finalize materials for each session
Facilitate each session and capture input
Debrief and summarize feedback for synthesis
Implementation Planning Session
Prepare draft roadmap structure
Task 3: Portfolio Development | Align roadmap steps with Hexagon Tool domains
Conduct session with discussion on implementation supports
Portfolio Outline
Building outline aligned to vision, guiding principles & model structure
Include draft format for “at-a-glance” summary
Deliver outline
Draft PSPH Portfolio to Project Committee
Integrate engagement session themes and draft logic model
Describe partner roles and essential components
Circulate full draft for Project Committee review
Project Committee Review
Compile and organize feedback by portfolio section
Clarify questions or inconsistencies with committee members
Project committee to submit feedback
Final PSPH portfolio
Incorporate revisions and finalize formatting
Submit to state leads and archive for future reference

## County & Tribal FFPS Tasks
2025 | [6 empty] | 2026 | [5 empty] | 2027 | [9 empty] | 2028 |  |  | Ongoing
| Jan | Feb | Mar | Apr | May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | April | May | Jun | July | Aug | Sep | Oct | Jan | Apr | Jul | Jan | Apr | Jul
Recruit, Train, and Support Expert Consultants and Tribal Representatives (Max of three)
CPP/CQI Leads select Lived &/or Community Experts, and Tribal Respresentative &/or Tribal Members and notify Chapin Hall of those selected. | bar: Jan to Mar
Counties orient and train Lived &/or Community Experts and Tribal Representatives &/or Tribal Members in county-specific FFPS implementation. | bar: May to 2026 July
Counties and Tribes notify Chapin Hall of any support needed to successfully engage Lived &/or Community Experts and Tribal Representatives &/or Tribal Members and develop strategies to address their needs. | bar: Jan to 2026 Sep
FFPS CQI Training
Counties and Tribes participate in FFPS CQI training. | bar: Apr to 2026 Sep
EBP Provider Contracting
Counties review and incorporate EBP contract guidelines into new and/or existing contracts. | bar: Jan to 2026 Sep
County and Tribal CQI Meetings
Counties and Tribes determine structure of FFPS county and Tribal CQI workgroups. | bar: May to 2026 Oct
Counties and Tribes determine members who will participate in FFPS county and Tribal CQI workgroups. | bar: May to 2026 Oct
Counties and Tribes convene FFPS CQI workgroups to share local EBP data, analyze challenges, and identify strategies. (Monthly year one; quarterly year two; and as data suggests need thereafter). | bar: 2026 July to Ongoing Jul
Regional Prevention CQI Collaborative (PCC)
Counties and Tribes determine members who will participate in quarterly PCC sessions. | bar: June to 2026 Oct
Counties and Tribes prepare local data, problem statements, and presentation materials with technical assistance support from Chapin Hall. | bar: 2026 Oct to 2027 Oct
Counties and Tribes participate in quarterly PCC sessions to support regional colleagues, share local EBP data, analyze challenges, and brainstorm strategies. | bar: 2026 Oct to 2027 Oct
CWS-CARES Backend Data Analysis
Counties and Tribes participate in consultation with Chapin Hall related to standardized FFPS data analystics to support CQI activities. | bar: 2026 July to 2026 Sep
Note on A20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Lexi Matter This statement doesn't make sense to me. Does it makes sense to you? I was thinking this should say something like... Using provider data, complete the bi-annual CARES Outcomes & Fidelity Report and email to FFPS Team for upload into backend of CARES
Note on H20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Lexi Matter The timing is off too. This would begin in March 2027 and occur every six months except for PAT which I think is too complicated to attempt to address in this visual. We could add rows if we want to get into the details of purveyor back=end upload or provider. Thoughts?